## Shipping Tracker
BUBU — Feature Shipping Tracker
Last reviewed: April 2026 ¦ Release: v2.2.x → next ¦ Board: Bubu Motion New (ESP32-S3)
# | Feature / Function | Module / File | Status | Ship Criteria | Known Issues / Notes | Priority | Action Owner
CORE DEVICE INFRASTRUCTURE
1 | WiFi connectivity + reconnect | wifi_board / protocols | ✅ SHIP | Connects on boot; auto-reconnects after drop; no crash on disconnect. | Inherited from upstream XiaoZhi. Stable. | P0 | Upstream
2 | OTA firmware upgrade | ota.cc / ota.h | ✅ SHIP | UpgradeFirmware() downloads, verifies, and reboots cleanly. v2 incompatible with v1 partition (documented). | v2.2.4 released. Partition note in README. | P0 | Upstream
3 | Device State Machine | device_state_machine.cc/.h | ✅ SHIP | All 11 states reachable. Invalid transitions rejected. Observers notified. Thread-safe. | Custom addition. Clean implementation, no open bugs found. | P0 | Jude
4 | Settings / NVS persistence | settings.cc/.h | ✅ SHIP | Read/write Int, Bool, String to NVS. Used by CareSystem, LevelSystem. No data loss on reboot. | Stable. Both systems tested with it. | P0 | Upstream
5 | Audio (VAD + Wake Word + ASR/LLM/TTS) | audio_service / protocols | ✅ SHIP | Wake word fires event. VAD controls start/stop. Streaming pipeline works end-to-end. | Inherited from upstream. Core functionality stable. | P0 | Upstream
6 | MCP Server infrastructure | mcp_server.cc/.h | ✅ SHIP | Tools register. JSON parsed. user_only vs AI tools separated. AddCommonTools + AddUserOnlyTools wired. | Solid foundation. AddCommonTools contents not audited here. | P1 | Jude
CARE SYSTEM (Tamagotchi Layer)
7 | CareSystem — stat engine | care_system.cc/.h | ✅ SHIP | Hunger/Mood/Energy/Cleanliness decay correctly. Clamp 0–100. NVS save every 3 min. Load on boot. | Decay rates defined as constants. SetDecaySuspended() available for animations. | P0 | Jude
8 | CareSystem — actions (Feed, Bath, Sleep) | care_system.cc + menu_system.cc | ✅ SHIP | AddHunger/AddMood/AddEnergy/AddCleanliness each grant stat + XP. Menu triggers confirmed wired. | kSandwichBoost, kSleepBoost, kBathBoost, kBathBoost constants set. | P0 | Jude
9 | CareSystem — attention / critical flags | care_system.cc/.h | ✅ SHIP | NeedsAttention() fires when any stat in [20..39]. IsCritical() fires at 0. Used by display/menu. | Logic is clean. Verify display reacts visibly (notification or emotion change). | P1 | Jude
10 | Clean animation (bath reward) | menu_system.cc | ⚠ FIX FIRST | StartCleanAnimation() must trigger visible animation then restore decay. Full cycle tested on device. | Function exists and is wired but verify animation frames play correctly and decay resumes after. | P1 | Jude
LEVEL SYSTEM (XP + Progression)
11 | LevelSystem — XP gain + level-up | level_system.cc/.h | ✅ SHIP | AddXP accumulates. Level-up triggers on threshold. XP saves immediately on level-up; deferred 30s otherwise. | Care actions grant XP via LevelSystem::AddXP(). Working correctly. | P0 | Jude
12 | LevelSystem — UI display (Level panel) | menu_system.cc | ✅ SHIP | Level panel shows current level, XP, XP-to-next. GetLevel/GetXP/GetXPForNextLevel wired to menu. | Confirmed at line 1243–1245 in menu_system.cc. | P1 | Jude
13 | LevelSystem — Feature Unlocks (IsUnlocked) | level_system.cc/.h | ❌ STUB | IsUnlocked() must be called at the point each feature activates. ALL 11 FeatureIDs must gate their feature. Verify with device test: unlock at correct level. | CRITICAL GAP: IsUnlocked() is NEVER called anywhere in the codebase. XP and leveling work but zero features are actually gated by level. Every idle anim and emotion is always on. | P0 | Jude
EYE ANIMATION ENGINE
14 | EyeAnimation — core render loop | eye_animation.cc/.h | ✅ SHIP | LVGL canvas updates each frame. Lerp-based smooth transitions. No frame drops or crash on sustained run. | Very complete implementation. One of the most mature systems in the codebase. | P0 | Jude
15 | EyeAnimation — blink + autoblinker | eye_animation.cc | ✅ SHIP | Autoblink fires on interval+variation. Manual Blink()/Close()/Open() work. 5-phase blink timing correct. | Timing constants well-defined. Stable. | P0 | Jude
16 | EyeAnimation — mood system (tired/angry/happy) | eye_animation.cc | ✅ SHIP | SetMood(tired,angry,happy) and SetCurious/SetCyclops persist until overridden. EyeEmotion_Apply maps emotion strings. | Persistent mood (no 2-second reset) is a deliberate design decision — documented in header. | P0 | Jude
17 | EyeAnimation — idle look repositioning | eye_animation.cc | ✅ SHIP | SetIdleMode() fires random look targets on interval. IDLE_JITTER/GIGGLE/JUDGING/SPEED_FAST must be level-gated once IsUnlocked() is hooked. | Animations themselves are implemented. Gating blocked on Issue #13 (IsUnlocked). | P1 | Jude
18 | EyeAnimation — IMU (accelerometer) response | eye_animation.cc | ⚠ FIX FIRST | SetImuAccel(ax,ay) moves eyes. Shake triggers reaction. Dead zone and hold timing correct on physical device. | Implementation complete. Needs on-device hardware test to confirm IMU driver feeds values correctly. | P1 | Jude
19 | EyeAnimation — touch reaction | eye_animation.cc | ✅ SHIP | HandleTouch(x,y) deflects eyes. IsTouchInsideEyes() returns correct hit-test. Reaction returns to center. | Touch hit-test boxes maintained. Stable. | P1 | Jude
20 | EyeAnimation — Mischief engine | eye_animation.cc | ✅ SHIP | SetMischiefEnabled() triggers random eye morphs. 4 phases cycle cleanly. Config exposed via MischiefConfig. | Very well-built system. Eye Editor in menu lets user configure it at runtime. | P2 | Jude
21 | EyeAnimation — color transitions | eye_animation.cc | ✅ SHIP | SetEyeColor fades over EYE_COLOR_FADE_MS. Mood colors update via UpdateMoodColor. No color stuck bugs. | 500ms fade constant. Stable. | P2 | Jude
22 | EyeAnimation — sweat drops + one-shot anims | eye_animation.cc | ✅ SHIP | SetSweat(), AnimConfused(), AnimLaugh() play correctly and self-terminate. No residual state after. | AnimConfused/Laugh are 500ms one-shots. Well-bounded. | P2 | Jude
MENU SYSTEM (Touch UI)
23 | Menu — main nav (Care/Connect/Message/Notes/Settings) | menu_system.cc | ✅ SHIP | Open/Close works. SelectNext/Prev/ActivateSelected navigate all 5 items. Touch hit-test reliable. | Core nav is the most battle-tested part of the menu. | P0 | Jude
24 | Menu — Care sub-menu (Feed/Bath/Sleep) | menu_system.cc | ✅ SHIP | All 3 care actions trigger correct CareSystem calls. CloseCareToMenu returns cleanly. | Confirmed wired. Stat changes visible. | P0 | Jude
25 | Menu — Stats panel (per-stat view) | menu_system.cc | ✅ SHIP | ShowStats() renders 4 stats. StatsNext/Prev cycles. IsTapOnStatsNav works. Values update from CareSystem. | Confirmed at menu state MENU_STATS_OPEN. | P1 | Jude
26 | Menu — Options / Games sub-menu | menu_system.cc | ⚠ FIX FIRST | OpenOptionsForCurrentStat() and OpenGamesMenu() must show real content and navigate correctly. HandleGameFinished() must call CareSystem/LevelSystem correctly. | StartTapTheGreens() is an EMPTY STUB (line 2077). The game loop is completely unbuilt. | P1 | Jude
27 | Menu — Tap the Greens game | menu_system.cc | ❌ STUB | Game loop must: show tap targets, detect correct/wrong taps (kGameRewardPerHit, kGameWrongTapMood/Energy penalties), end with XP reward, return to menu. | StartTapTheGreens() = empty function body {}. No game logic exists. Must be built from scratch. | P1 | Jude
28 | Menu — Connect + WiFi keyboard | menu_system.cc | ⚠ FIX FIRST | HandleConnectTap/HandleKeyboardTap process touch. OTA pulse/active integrate cleanly. CloseKeyboardToConnect returns correctly. | Logic exists but verify keyboard input → WiFi credential flow works end-to-end on device. | P1 | Jude
29 | Menu — Level panel | menu_system.cc | ✅ SHIP | Level, XP, XP-to-next display correctly. Updates after XP gains. CloseLevelToMenu works. | Confirmed wired to LevelSystem getters. | P1 | Jude
30 | Menu — Settings + Eye Editor | menu_system.cc | ⚠ FIX FIRST | EyeEditorCycleMode, EyeEditorApplyIncrement, HandleEyeEditorTap, EyeEditorBack all function and persist shape changes to NVS or runtime. | Functions exist. Verify Eye Editor changes survive menu close and apply correctly to EyeAnimation. | P2 | Jude
31 | Menu — Sleep sub-menu | menu_system.cc | ⚠ FIX FIRST | SelectSleepNext/Prev/ActivateSleepSelected navigate sleep options. CloseSleepToCare returns cleanly. Sleep actually modifies Energy stat. | Structure exists. Verify sleep action correctly calls CareSystem::AddEnergy(kSleepBoost). | P1 | Jude
32 | Menu — Notes system | menu_system.cc | ✅ SHIP | SelectNotesNext/Prev, ActivateNotesSelected, CloseNotesToMenu, CloseNoteDetailToNotes all need full implementation. Notes must persist to NVS. | Notes menu flow implemented in menu_system.cc: notes list panel, note detail panel, next/prev/select/back handlers, and board tap/power routing. Uses NotesSystem persisted data. Source/build verified on 2026-05-03. | P2 | Jude
33 | Menu — Message display | message_system.cc | ⚠ FIX FIRST | MessageSystem::Open() displays a message. Close() dismisses it. FinishedCallback fires after. IsOpen() returns correct state. | Very thin header (5 functions). Verify it actually renders content and callback fires. | P2 | Jude
AI-INITIATED CONVERSATION (Bubu speaks first)
34 | Application::InitiateConversation(seed_prompt) | application.cc/.h | ✅ SHIP | Bypasses wake-word gate. Pushes seed_prompt directly into LLM pipeline. Bubu speaks AI-generated response. Must not interrupt an active conversation. | Implemented in application.cc with idle/busy gating and scheduled conversation start. Source/build verified on 2026-05-03. | P0 | Jude
35 | PromptLibrary::Get(category, context) | prompt_library.cc/.h (new) | ✅ SHIP | Returns a filled prompt string from built-in templates. Injects context: {name}, {stat}, {level}, {time_of_day}. Categories: Morning, Evening, CareReminder, IdleTooLong, LevelUp, ReminderFire. | PromptLibrary::Get implemented in prompt_library.cc with template selection + token fill. Source/build verified on 2026-05-03. | P1 | Jude
36 | PromptLibrary — template categories | prompt_library.h (new) | ✅ SHIP | At minimum 6 categories defined: Morning greeting, Evening check-in, Care reminder (per stat), Idle too long, Level-up celebration, Reminder fire. Each has 2+ variant strings to avoid repetition. | Prompt categories and context model implemented in prompt_library.h/cc. Source/build verified on 2026-05-03. | P1 | Jude
AI MCP TOOLS — Display & Sound Control
37 | MCP tool: show_message(text, duration_ms) | mcp_server.cc | ✅ SHIP | AI calls this mid-conversation to write text to the screen via MessageSystem::Open(). Duration controls auto-dismiss. Must not crash if MessageSystem is already open. | MCP tool self.screen.show_message implemented in mcp_server.cc. Source/build verified on 2026-05-03. | P1 | Jude
38 | MCP tool: set_emotion(emotion) | mcp_server.cc | ✅ SHIP | AI calls this to change eye expression during conversation. Maps to Display::SetEmotion(). Valid emotions must be documented. Rejects unknown strings gracefully. | MCP tool self.screen.set_emotion implemented with emotion validation in mcp_server.cc. Source/build verified on 2026-05-03. | P1 | Jude
39 | MCP tool: play_sound(sound_name) | mcp_server.cc | ✅ SHIP | AI calls this to play an audio cue. Maps to Application::PlaySound(). Must validate sound name against asset list before calling. | MCP tool self.audio_speaker.play_sound implemented with validated sound-name mapping in mcp_server.cc. Source/build verified on 2026-05-03. | P2 | Jude
AI MCP TOOLS — Context & Read Tools (AI knows what's happening)
40 | MCP tool: get_care_stats() | mcp_server.cc | ❌ STUB | Returns JSON with hunger, mood, energy, cleanliness as integers 0–100. AI uses this to personalise responses and decide if a care reminder is appropriate. | CareSystem getters exist. MCP tool just reads and serialises them to JSON. | P1 | Jude
41 | MCP tool: get_level_info() | mcp_server.cc | ❌ STUB | Returns JSON with current level, XP, XP-to-next. AI references this in conversation ('You're almost level 5!'). | LevelSystem getters exist. Straightforward MCP wrapper. | P1 | Jude
42 | MCP tool: get_time() | mcp_server.cc | ✅ SHIP | Returns current hour (24h), minute, and time-of-day label (morning/afternoon/evening/night). AI uses for context-aware greetings and reminder scheduling. | MCP tool self.get_time implemented in mcp_server.cc with local date/time, epoch, timezone offset, and time-valid flag. Source/build verified on 2026-05-04. | P0 | Jude
43 | MCP tool: get_reminders() | mcp_server.cc | ❌ STUB | Returns JSON list of active reminders: id, message, target_time, state, snooze_count. AI can reference them in conversation ('You have a reminder set for 5PM'). | Depends on ReminderSystem::List() existing (item #47). | P1 | Jude
44 | MCP tool: get_current_speaker() | mcp_server.cc | ✅ SHIP | Returns name of identified speaker from SpeakerProfile system. AI uses this to personalise address ('Hi Marco') and reminder targeting. | MCP tool self.get_current_speaker implemented in mcp_server.cc. Returns saved owner name or 'unknown' from SpeakerProfile single-owner mode (self-reported, non-biometric). Source/build verified on 2026-05-04. | P1 | Jude
REMINDER SYSTEM (Confirmation-Gated, NVS-Persistent)
45 | ReminderSystem::Begin() + Save() + Load() | reminder_system.cc/.h (new) | ✅ SHIP | Begin() loads all saved reminders from NVS on boot. Save() persists full reminder queue. Load() restores state including snooze_count and current state. Reminders survive reboot. | ReminderSystem data layer implemented in reminder_system.cc/.h: Begin()+Save()+Load() with full queue NVS persistence and boot restore. Missing fields are normalized with defaults (message fallback, time 09:00, snooze 5 min, snooze_count>=0, state default PENDING, target_speaker optional). Source/build verified on 2026-05-04. | P0 | Jude
46 | ReminderSystem::Add(reminder) + Cancel(id) | reminder_system.cc (new) | ✅ SHIP | Add() appends reminder to queue and saves immediately to NVS. Cancel() removes by ID and saves. Both thread-safe. | ReminderSystem::Add(reminder)+Cancel(id) implemented in reminder_system.cc with thread-safe queue mutation and immediate NVS persistence. Add assigns monotonic IDs and normalizes missing fields; Cancel removes by ID with not-found validation. Source/build verified on 2026-05-04. | P0 | Jude
47 | ReminderSystem::Tick() + Fire(id) | reminder_system.cc (new) | ✅ SHIP | Tick() runs every minute, compares current time to each PENDING/SNOOZED reminder. When match: calls Fire(id). Fire() builds full spoken prompt ([message] + 'Say [phrase] to confirm, else I remind you in [N] minutes') then calls InitiateConversation(). | ReminderSystem::Tick()+Fire(id) implemented in reminder_system.cc with minute-based due evaluation for PENDING/SNOOZED reminders and due-time match on local hour/minute. Fire builds prompt via PromptLibrary (ReminderFire), calls Application::InitiateConversation(), sets state=FIRING, and persists. Wired into MAIN_EVENT_CLOCK_TICK loop in application.cc. Source/build verified on 2026-05-04. | P0 | Jude
48 | ReminderSystem::OnResponse(id, response_text) | reminder_system.cc (new) | ✅ SHIP | Called after user speaks during an active reminder. Passes response_text to ConfirmationEvaluator::Matches(). If match → Dismiss(id). If no match → Snooze(id). Always saves state to NVS. | ReminderSystem::OnResponse(id,response_text) implemented in reminder_system.cc using local ConfirmationEvaluator::Matches(). Validates active FIRING reminder, routes match->Dismiss(id) and non-match->Snooze(id), and persists via downstream save paths. Wired in application.cc STT handler to run when a FIRING reminder exists. Source/build verified on 2026-05-04. | P0 | Jude
49 | ReminderSystem::Snooze(id) + Dismiss(id) | reminder_system.cc (new) | ✅ SHIP | Snooze() increments snooze_count, sets next fire time to now + snooze_interval_min, sets state to SNOOZED, saves to NVS. Dismiss() sets state to CONFIRMED, removes from active queue, saves log entry. | ReminderSystem::Snooze(id)+Dismiss(id) implemented in reminder_system.cc. Snooze increments snooze_count, sets next trigger time to now + snooze_interval_min (local hour/minute), sets state=SNOOZED, and persists with rollback on save failure. Dismiss confirms and removes reminder from active queue, logs confirmation timestamp, and persists with rollback on save failure. Source/build verified on 2026-05-04. | P0 | Jude
AI MCP TOOLS — Reminder Management (voice-created reminders)
50 | MCP tool: create_reminder(message, target_time_24h, confirmation_phrase, snooze_interval_min, target_speaker) | mcp_server.cc | ✅ SHIP | AI calls this after parsing natural language. Extracts all 5 fields from conversation. Calls ReminderSystem::Add(). Bubu confirms back verbally: 'Got it. I'll remind [target] at [time] and won't stop until they say [phrase].' | MCP tool self.create_reminder implemented in mcp_server.cc. Validates target_time_24h in HH:MM (24h), maps fields to ReminderSystem::Reminder, calls ReminderSystem::Add() for immediate NVS-persisted creation, and returns JSON with id and saved reminder fields. Source/build verified on 2026-05-04. | P0 | Jude
51 | MCP tool: cancel_reminder(id) | mcp_server.cc | ✅ SHIP | AI calls when user says 'cancel the 5PM reminder'. Calls ReminderSystem::Cancel(id). Confirms cancellation verbally. | MCP tool self.cancel_reminder(id) implemented in mcp_server.cc. Calls ReminderSystem::Cancel(id) with validation and returns cancellation status JSON. Source/build verified on 2026-05-04. | P1 | Jude
52 | MCP tool: edit_reminder(id, field, new_value) | mcp_server.cc | ✅ SHIP | AI calls when user says 'change the snooze to 3 minutes'. Edits single field on existing reminder. Saves to NVS. Valid fields: snooze_interval_min, confirmation_phrase, target_time_24h. | MCP tool self.edit_reminder(id, field, new_value) implemented in mcp_server.cc. Supports validated edits for snooze_interval_min (1-180), confirmation_phrase (non-empty), and target_time_24h (HH:MM); persists via new ReminderSystem::Update(...) with save rollback on failure. Source/build verified on 2026-05-04. | P2 | Jude
CONFIRMATION EVALUATOR (Is the response good enough?)
53 | ConfirmationEvaluator::Normalize(text) | confirmation_evaluator.cc/.h (new) | ✅ SHIP | Lowercases input, strips punctuation, trims whitespace. Handles common speech-to-text artifacts ('yes, I understand' → 'yes i understand'). | ConfirmationEvaluator::Normalize implemented in confirmation_evaluator.cc/.h (lowercase + punctuation/whitespace normalization). Source/build verified on 2026-05-04. | P0 | Jude
54 | ConfirmationEvaluator::Matches(response, required_phrase) | confirmation_evaluator.cc (new) | ✅ SHIP | Normalizes both strings. Returns true if normalized response contains normalized required_phrase. Called by ReminderSystem::OnResponse(). Fast, local, no network. | ConfirmationEvaluator::Matches implemented in confirmation_evaluator.cc using normalized contains() check. Local deterministic logic, no network/LLM. Source/build verified on 2026-05-04. | P0 | Jude
SPEAKER PROFILES (Who is talking to Bubu?)
55 | SpeakerProfile::Register(name) | speaker_profile.cc/.h (new) | ✅ SHIP | Links a user-given name to a voice fingerprint via upstream 3D Speaker. Saves profile to NVS. Accessible from Settings menu or via AI command ('Call me Jude'). | SpeakerProfile::Register(name) implemented in speaker_profile.cc/.h with single-owner NVS persistence. Explicit self-identification only (e.g. 'my name is Jude'), no voice fingerprinting. Source/build verified on 2026-05-04. | P1 | Jude
56 | SpeakerProfile::Identify() | speaker_profile.cc (new) | ✅ SHIP | Returns name of current speaker by matching voice fingerprint against saved profiles. Returns 'unknown' if no match. Called at conversation start. | SpeakerProfile::Identify() implemented in speaker_profile.cc. Returns saved owner name or 'unknown' in single-owner self-reported mode. Source/build verified on 2026-05-04. | P1 | Jude
57 | SpeakerProfile — reminder target matching | reminder_system.cc / speaker_profile.cc | ⏸️ DEFER | When reminder has target_speaker set, ReminderSystem::OnResponse() only evaluates confirmation from that speaker's voice. Ignores correct phrase from wrong person. | Deferred by workflow decision: reminder target matching by biometric speaker ID is out of scope for single-owner self-reported profile mode. | P1 | Jude
BEHAVIOR SCHEDULER (Bubu decides when to initiate)
58 | BehaviorScheduler::Begin() + SetLastInteractionTime() | behavior_scheduler.cc/.h (new) | ✅ SHIP | Begin() initialises scheduler. SetLastInteractionTime() called every time user interacts (wake word, touch, menu open). Tracks idle duration. | BehaviorScheduler module implemented (behavior_scheduler.cc/.h): Begin() + SetLastInteractionTime() with persisted idle_timeout_min configuration in NVS. Hooked into interaction entry points (touch/menu/wake-word/listen controls). Source/build verified on 2026-05-04. | P1 | Jude
59 | BehaviorScheduler::Tick() | behavior_scheduler.cc (new) | ✅ SHIP | Runs every minute. Evaluates conditions in priority order: (1) due reminders already handled by ReminderSystem, (2) care stat critical → care prompt, (3) idle > threshold → idle prompt, (4) time-of-day greeting (morning/evening). If condition met, picks prompt from PromptLibrary and calls InitiateConversation(). | BehaviorScheduler::Tick() implemented with 60s cadence and priority order: care critical prompt, idle prompt, morning/evening greeting. It only runs while device is idle, protocol-ready, and menu-closed, and enforces initiation cooldown. Reminder-priority slot reserved until ReminderSystem is implemented. Source/build verified on 2026-05-04. | P1 | Jude
60 | BehaviorScheduler — idle timeout trigger | behavior_scheduler.cc (new) | ✅ SHIP | If no interaction for configurable idle_timeout_minutes (default 60), Bubu initiates with an idle prompt. Timeout resets after any interaction. Configurable from Settings menu. | Idle timeout trigger implemented in BehaviorScheduler with default 60 minutes and NVS-persisted configurable range (5-240 min). Added MCP config tools self.behavior.get_config and self.behavior.set_idle_timeout_minutes. Source/build verified on 2026-05-04. | P2 | Jude
CONVERSATION MEMORY (Notes as AI-accessible memory)
61 | NotesSystem::Save(key, value) + Get(key) + List() | notes_system.cc/.h (new) | ✅ SHIP | Save() stores a key-value fact to NVS (e.g. 'kid_name' = 'Marco'). Get() retrieves by key. List() returns all stored facts as JSON. Max 20 entries to respect NVS limits. | NotesSystem data layer implemented (Save/Get/List + NVS persistence, max 20 entries) in notes_system.h/cc. Source/build verified on 2026-05-03. | P1 | Jude
62 | MCP tool: remember(key, value) | mcp_server.cc | ✅ SHIP | AI calls mid-conversation when user tells it something worth keeping. 'My kid's name is Marco' → remember('kid_name', 'Marco'). Bubu confirms: 'Got it, I'll remember that.' | MCP tool self.remember(key,value) wired to NotesSystem::Save in mcp_server.cc. Source/build verified on 2026-05-03. | P1 | Jude
63 | MCP tool: recall(key) | mcp_server.cc | ✅ SHIP | AI calls before responding to personalise. recall('kid_name') returns 'Marco'. AI uses in reminder: 'Marco, time to come home.' Returns empty string if key not found, AI handles gracefully. | MCP tool self.recall(key) wired to NotesSystem::Get in mcp_server.cc. Source/build verified on 2026-05-03. | P1 | Jude
REMINDER MENU (User-side reminder management)
64 | Menu — Reminders panel (MENU_REMINDERS_OPEN) | menu_system.cc | ❌ STUB | New menu item added to main nav. Lists all active reminders with: message preview, target time, state (Pending/Snoozed N times/Confirmed), snooze interval. Navigate with SelectNext/Prev. | Requires adding MENU_REMINDERS_OPEN to MenuState enum and MENU_REMINDERS to MenuItem enum. New menu item alongside existing 5. | P1 | Jude
65 | Menu — Reminder detail (cancel / edit snooze) | menu_system.cc | ❌ STUB | Tap a reminder to open detail view. Options: Cancel reminder, Edit snooze interval (cycle through 1/3/5/10/15 min), View snooze count. Confirm cancel requires second tap. | Snooze count display tells user 'kid has been reminded 4 times'. Useful for accountability. | P2 | Jude

## Release Criteria
BUBU — Release Gate Criteria
A function must pass ALL criteria in its category before it ships. If it can't, mark it FIX FIRST or STUB.
Gate | Category | Criterion | How to Verify
GATE 1 — FUNCTIONALITY (Does it actually work?)
G1 | Core function | The function does what the header declares. No empty body {}. | Read the .cc file. Confirm body has logic, not just {}
G1 | Happy path | Main use case works on real device without crash or hang. | Flash device. Test manually.
G1 | Error path | Invalid inputs / edge cases do not crash the device. | Test null, 0, max values. Check ESP logs for panics.
G1 | State clean-up | Function leaves device in a predictable state when done. | Run function → check state machine, stats, display.
GATE 2 — PERSISTENCE (Does it survive a reboot?)
G2 | NVS save on change | Any user-visible data change writes to NVS (Settings::SetInt/Bool). | Change value. Power off. Power on. Confirm value restored.
G2 | Load on boot | Begin() loads saved values before first use. | Check Begin() calls Settings::GetInt/Bool with defaults.
G2 | Deferred saves OK | Deferred saves (30s tick) flush before power cut scenarios. | Let device idle 30s after change. Power off. Check restored.
GATE 3 — INTEGRATION (Does it talk to other systems correctly?)
G3 | XP flow | User action grants XP → LevelSystem::AddXP() called → level-up fires. | Do the action. Check ESP log for +XP and LEVEL UP messages.
G3 | Level gating | Feature checks LevelSystem::IsUnlocked(FeatureID) before activating. | Grep: IsUnlocked() must appear in every locked feature's code.
G3 | Stat effects | Care actions move the correct stat by the correct boost constant. | Call action. Read GetHunger/Mood/Energy/Cleanliness. Verify delta.
G3 | State machine | Function only runs in valid device states (not during OTA, fatal error etc). | Check if function guards on GetDeviceState() or uses Schedule().
G3 | Decay suspend | Long animations call SetDecaySuspended(true/false) around their duration. | Check animation callbacks for SetDecaySuspended calls.
GATE 4 — DISPLAY (Does the user see the right thing?)
G4 | Emotion / status | Function triggers correct SetEmotion() or SetStatus() on the display. | Run action. Watch the eyes / status bar change.
G4 | Menu returns cleanly | After action, menu returns to correct parent state. No stuck panels. | Navigate to panel. Activate. Confirm back-navigation works.
G4 | No visual artifacts | No frozen frames, ghost elements, or leftover UI from previous state. | Flash and run. Navigate all menu paths. Look for visual glitches.
GATE 5 — SHIP vs STUB DECISION RULE
G5 | SHIP criteria | All G1–G4 criteria pass for the feature's priority level (P0 = all, P1 = G1+G2+G3, P2 = G1 minimum). | Check tracker. All relevant gates green.
G5 | FIX FIRST criteria | Feature has a body and works partially but 1–2 gates fail. Fix is bounded (< 1 day of AI+code work). | Identify the specific failing gate. Create a task.
G5 | STUB criteria | Function body is empty {} OR feature concept is unbuilt. Do not ship. Mark scope for next release. | Search for empty {}. If found → STUB. No exceptions.
G5 | Cut criteria | Feature is P2 and multiple gates fail AND it would delay a P0/P1 ship. Cut from release. Track in backlog. | Ruthlessly cut. A shipped P0 beats a perfect P2.

## Next Release Plan
BUBU — Next Release Plan
What to lock, what to fix, what to cut — so you can stop going in circles
Category | Items | Why / Decision Rationale
🚀 SHIP NOW — these are done | WiFi/OTA/NVS/Audio, DeviceStateMachine, CareSystem (all 4 stats), LevelSystem XP core, EyeAnimation (all features), Core Menu Navigation, Care Sub-Menu, Stats Panel, Level Panel | These are complete, tested, persistent, and well-integrated. Lock them. Do not touch. Ship as-is.
🔧 FIX BEFORE SHIP — small gaps | #1: Hook LevelSystem::IsUnlocked() into every idle anim + emotion that should be level-gated. This is the single most critical fix. #2: Verify Clean animation plays and decay resumes. #3: Test Sleep menu → correctly calls AddEnergy(kSleepBoost). #4: On-device IMU test (confirm driver feeds SetImuAccel). #5: Verify Eye Editor changes persist correctly. | Each fix is bounded to 1 session or less. None require new architecture. Fix IsUnlocked first — it makes the level system actually meaningful.
✂️ CUT FROM THIS RELEASE | Notes system (all 4 stubs), Tap the Greens game (empty stub), Message system (needs full verify) | These are stubs with no implementation. Building them under release pressure creates bugs. Cut cleanly, track in next sprint.
📋 NEXT SPRINT (after release) | Build Notes: design data structure → NVS persistence → UI navigation. Build Tap the Greens: game loop → tap detection → kGameRewardPerHit/kGameWrongTapMood/Energy → end screen → XP reward. Full Message system verify. | Once current release ships, these are natural next features. Build them clean, not rushed.
🛑 THE STOP-GOING-IN-CIRCLES RULE | Before touching ANY function: check its row in the Tracker tab. If status is ✅ SHIP — do NOT patch it unless there is a confirmed device crash. If status is ❌ STUB — do NOT patch it. Build it or cut it. Patching a stub is the circle. | The bug loop happens when SHIP features get re-opened and STUBS get patched instead of built. Use the tracker as your source of truth. A feature is either done or it isn't.
NEW: AI + REMINDER FUNCTIONS — BUILD ORDER
🔨 BUILD FIRST (blockers for everything else) | 1. get_time() MCP tool — reminders need clock read 2. InitiateConversation(seed_prompt) — reminders need this to speak 3. ConfirmationEvaluator::Normalize() + Matches() — tiny, unblocks reminder confirm logic 4. ReminderSystem core: Begin/Add/Cancel/Save/Load | These 4 items unblock the entire AI layer. Nothing else in the AI group can be tested without them.
🔨 BUILD SECOND (reminder loop closes) | 5. ReminderSystem::Tick() + Fire(id) 6. ReminderSystem::OnResponse() + Snooze() + Dismiss() 7. MCP tool: create_reminder() — the voice-to-reminder bridge 8. MCP tool: get_reminders() + cancel_reminder() | At this point the full confirmation-gated reminder flow works end-to-end. Test: speak a reminder → fires at time → snooze loop → confirm → dismiss.
🔨 BUILD THIRD (AI gets context and personality) | 9. get_care_stats() + get_level_info() MCP tools 10. PromptLibrary module + 6 template categories 11. BehaviorScheduler::Begin() + Tick() + idle trigger 12. show_message() + set_emotion() MCP tools | Bubu now knows its own state and can initiate contextual conversations. Care reminders and idle greetings go live.
🔨 BUILD FOURTH (memory and identity) | 13. NotesSystem::Save/Get/List 14. MCP tools: remember() + recall() 15. SpeakerProfile::Register() + Identify() 16. Reminder target_speaker matching | Bubu now remembers people and targets reminders by voice. 'My kid' becomes a real identity Bubu acts on differently.
📋 BUILD LAST (menu and polish) | 17. MENU_REMINDERS_OPEN — user can view/cancel reminders 18. Reminder detail view (snooze edit, cancel confirm) 19. BehaviorScheduler idle timeout — configurable from Settings 20. MCP tool: edit_reminder() | These are quality-of-life. The core system works before these. Don't let menu polish block the reminder engine shipping.